## Slide 1: Scrum Project: Eco-Factory
University Scrum Simulation
Team of 4 Members
Scrum Master: Sadia
Product Owner: Sajib
Dev Team: Nihon, Tawheed

## Slide 2: Product Backlog
- Factory Building (structure, utilities, machinery)
- Employee Housing (apartments, family houses)
- Grocery Store
- Daycare Center
- Sports Center
- Sustainability Features (eco-materials, renewable energy)
- Roads, Landscaping, and Community Facilities

## Slide 3: Sprint 1 (Weeks 1–4): Foundation & Setup
- Site preparation & land leveling
- Factory foundation work
- Housing layout & foundation
- Draft design for grocery store & daycare
- Sustainability planning (materials, energy source)
Deliverables:
✅ Factory & housing foundations completed
✅ Community design plan ready
✅ Approved eco-strategy

## Slide 4: Sprint 2 (Weeks 5–8): Construction Progress
- Factory walls & structure setup
- Install utility lines (electricity, water, solar)
- Start grocery store construction
- Daycare structure foundation
- Roads and pathways planning
Deliverables:
✅ Factory structure standing
✅ Utilities functional
✅ Grocery store half-built
✅ Daycare construction started

## Slide 5: Sprint 3 (Weeks 9–12): Completion & Handover
- Complete factory interiors (machinery installation, safety)
- Finish grocery store, daycare, and sports center
- Complete housing units
- Landscaping, roads, and community facilities
- Testing & final inspection
Deliverables:
✅ Factory ready for use
✅ Housing completed
✅ Grocery store, daycare, and sports center operational
✅ Sustainable community ready